## Sheet1
Sr. No. | Module | Observations and new development | Remark by Parth | Estimated Days | Status | Developer
1 | Employee logger | Post grant approval, after receiving the email, employee needs to acknoledge the same and it will get stored in database. | a check box where the employee needs to check & a User log report with employee details / Date & time to be downloadable by admin) | 2
2 | Admin Grant | Creation of Grant with single employee - Admin is not able to see in the vested Grant in the admin tab for the approval. |  | 1 | Done | Prashant
3 | Admin Email | Email Config - Changes in design, adding rolewise email option. it should be editable. |  | 2 | Done | Ashraf
4 | Emp Exercise | To remove cancle cheque from the exercise screen. |  | 2 | Done | Prashant
5 | Emp Exercise | On Preview page, section name should be in one line. |  | 1 | Done | Prashant
6 | Emp Exercise | Total Number of Exercise should be as per the dashboard. |  | 1 | Done | Prashant
7 | Admin Exercise | Name Change to >> upload Bank statement on Exercise. |  | 1 | Done | Prashant
8 | Admin Exercise Report | To add new columns in exercise report. |  | 1 | Done | Prashant
9 | Admin | After the creation of Grant, it will go for checker(New role has to define) then it will go to the Hr head. |  | 5
10 | Admin | Employee Edit option to be implemented same as PMS.(Only for the ESOP users)(List of fields would be provided by the Parth) On HRMS DB Sync page. | Shared in sheet -> "Emp Details" | 3
11 | Emp Exercise | To remove popup on exercise page. |  | 1 | Done | Prashant
12 | Emp Exercise | If user has completed exercise two times in a day >> It should be display in Secreterial page in same Tranche and vesting(in single row). Also validation for Bank statement to be available for second transaction also. or If user is doing two transaction in 2 days>> One new page needs to be added for admin, inside the Exercise tab >> To reejct this transaction >> Stating that please do all the transaction at a time.(Employee's transactions will get rolled out) | Admin Exercise approval page needs to be created under all scenarios Once the employee submits the exercise it should go the admin exercise page Admin will approve or reject the exercise (Only approved transactions to be recorded in the the exercise report) once the process is completed admin will upload the bank statement & submit for secreterial approval | 4
13 | Emp Sell | To check auto Save functionality on sell page. |  | 1
14 | Admin Sell approval | Number of sale on the admin sale approval(ticker)page displaying wrong. |  | 1
15 | Emp Sell | New section as Upload transaction receipt to be added on Emp sell page. (mandatory). |  | 2
16 | Emp Sell | User can do the sell transaction only once, with current window. Sell option will be non-editable after one transaction for current window. If admin reject the sell transanction (in any case) then only user will be able to do the transaction for the ongoing sell window. |  | 3 | WIP | Prashant
17 | Admin Sell | To provide new functionality for admin for sell transaction rejection. |  | 3
18 | Admin Lapse | Admin dashboard to be display on with new tab(Lapse), employeewise data availabe in the ESOP system. Admin will be able edit and update the number of ESOP for LAPSE with respect to the employee. |  | 3
19 | Admin PDF Password | PDF password will be as PAN Card and Adhar Card. |  | 1 | Done | Prashant
20 | Admin Proxy Window Resize | Resize the Proxy window as per the PMS |  | 1
|  |  | Total Days | 39 | 15 | Development with 2 dev 15th October, parallel UAT testing.
|  |  | Production Deployment | 7 | 7 | Production Deployment from 16th of October 2021 and testing from our end.
|  |  |  | Total Days | 22

## Emp Details
Employee Code | Employee status | Emp Name | Date of joining | Grade | Business Department | Function | Cost Centre | Reporting manager code | Reporting manager | HOD Emp Code | HOD Name | BH Emp Code | BH Name
111111 | Active | XXXXX | 2020-08-15 | SM1 | IT | IT | IT - Strategic Initiatives | 11111 | YYYYY